## Front-end
Subjects | View | Functions | Short Description | Designed | Notes | Estimate (Hours) | DS Comments
Agency Home Page |  | Agency Login Page |  |  |  | 4
|  | Top menu | Left: Agency name @ Email | Right: Curency -Livechat - Profile -Logout |  | 2 | We will consider script for live chat, which you will provide. We will consider the language section in phase 2.
|  | Main menu | Left: Our Logo | Right: ACCOMMODATION TRANSFERS TOURS ACTIVITIES CRUISES PACKAGES |  | 2
| http://prntscr.com/hey24u | Main content | Account status | http://prntscr.com/hey3ow |  | 16 | We will display the particular Agency booking information with search functionality
|  |  | Supper Deals | http://prntscr.com/hey4g7 |  | 4 | Admin will upload the banner on this deals and if we will click on particular deal then will redirect on any link which link will be set by the admin.
|  | Footer | Left: Home FAQs Contact Us Terms & Conditions Privacy Policy | Right: Icon: Facebook youtube Twitter Google+ |  | 0.5
|  |  | Bottom centre: | http://prntscr.com/hey7kq |  | 0.5
Booking data
Accommodation Home Page |  | Accommodation |  | http://prntscr.com/hdljxj |  | 4 | When user client on the accomodation tab then will display the search box.
|  |  | Ajax Search | http://prntscr.com/hdlk32 |  | 4 | We will pull the destination list from database using ajax search. Also we will put all the destination in cache to retrieve the quickly.
|  |  |  | http://prntscr.com/hdlkar |  | 32 | When user will click on search button then we will pull the results from Hotel API, which you will provide. All information will depends on the API.
|  |  | Search result | http://prntscr.com/hg4f86 | more search option | 12 | Filter functionality on hotel result page as prices, property type, areas, start rating and hotel name.
|  |  | Hotel API Integration |  |  | 40 | We will consider the single hotel API to pull the data and check the availability.
| http://prntscr.com/heykj0 |  | Hotel on sale -Acommodation home page | http://prntscr.com/hdljrf |  | 12 | User will see the pupular hotels on this page, which will manage from admin panel. When we click on the book now button then will redirect on details page and display the room information. User can check the availablity from API on this page.
|  |  | Hotel display hotels | http://prntscr.com/hg5k8l |  | NA | We are assuming that page will be the same as hotel result page. So I think, we don't require to create new page.
|  |  | Hotel details - when click and choose the hotel they want | http://prntscr.com/hdlklj |  | 16 | Create this page with hotel and room type information. Agent can choose the particular room for booking.
|  |  | Trip Advisor API |  |  | 8 | We will integrate the trip advisor location API to get the location id of each hotel and will display the reviews accordingly on this page.
|  |  | Book process - select the room they want to book | http://prntscr.com/hdlkol |  | 16
|  |  | Book form - fill out the details and process booking | http://prntscr.com/hdlkt6 |  | 16 | Agent will fill up the booking details with passenger information. We will also display the selected hotel and room type information.
|  | all this step will be ADD the same with all our products | Confirmed Quote - After filled out the information | http://prntscr.com/hfp7a7 |  | 16 | Display the booking details for generate the quote.
|  |  | ADD products - If clents want to continues shopping | http://prntscr.com/hfph91 |  | 8 | Agent can add the another product into this quote as Activities, Transfer, Cruise.
|  |  | Print out their itinerary or Sumary of their booking- DO NOT want to continues shopping | http://prntscr.com/hfpi4b | convert to DPF so they can email or print or Save | 8 | Send email, print out and save the booking.
|  |  | Booking confirmed- payment option | http://prntscr.com/hfpu8g | They can choose to net for gross amount | 4 | User can choose the payment option and pay the amount accoding to the selection of Net and Gross amount.
|  |  | Booking confirmed- print out their invoice or tinerary or voucher | http://prntscr.com/hfpupj | convert to DPF so they can email or print or Save | 8 | Print the booking invoice
|  |  | Payment Gateway Integration |  |  | 16 | We are considering Paypal payment gateway to take the payment from customer. If we need any other then we will consider it later and update the time accordingly.
Activities Home page |  | Activities | Search and activities list display | http://prntscr.com/hfq53i |  | 8 | When user click on activity tab then will display the search box, from where user can search the activity according to the destination
|  |  | Activities displayafter search | http://prntscr.com/hg5k8l |  | 16 | Display the searched activity list as hotel result page. We will consider the activity API to get the records.
|  |  | Activity API Integration |  |  | 24 | For now, we will consider the single API, which you will provide us.
| http://prntscr.com/hfq1zb |  | Activities details display in single selection | http://prntscr.com/hg4jlh |  | 16 | Display the activity details with check availablity feature
| http://prntscr.com/hfq4fn |  | After selection and display price | http://prntscr.com/hg4kx1 |  | 8 | Provide the edit availablity functionality
|  |  | Details about the package | http://prntscr.com/hg4w1y |  | 8 | Display the whole activity details which depends on the API data
| http://prntscr.com/hfq3rg |  | Activities available checked and process | http://prntscr.com/hdllhz |  | 4 | Checked the activity availablity
|  |  | Activities book form | http://prntscr.com/hdlltx |  | 8 | Display the selected activity details and passenger information for booking.
|  |  | Booking process |  |  | 8 | Use the booking process same as hotel
|  | Transfers | Search form | http://prntscr.com/hdlmhd |  | 16 | Tranfer search box, we will pull the pick up and drop off information from admin.
Transfer Home page | http://prntscr.com/hdlm24 |  | Search result | http://prntscr.com/hdlmlk |  | 20 | Display the transfer details on this page, we will pull the data from third party API.
|  |  | Tranfer API Integration |  |  | 20 | Integrate the provided transfer API
|  |  | Book form | http://prntscr.com/hdlmqd |  | 16 | Display the selected transfer details on this with passenger details, we will only display the transfer information on this page when we will select transfer instead of vessel.
|  |  | Booking process |  |  | 8 | Use the booking process same as hotel
|  | Cruise | Cruise selection | http://prntscr.com/hg57zj |  | 8 | Display the cruise list from database
|  |  | Details of search | http://prntscr.com/hg5g46 | add on option search for cruise line if they know the cruise mane and add on option fill out by duration | 8 | When we click on particular cruise then display the search box to search the cruises according to the availablity.
Cruise Home Page |  |  | Cruise display after search | http://prntscr.com/hg5k8l |  | 24 | Cruise listing page according to the hotel layout. We will pull the cruise information from API.
|  |  | Cruise API Integration |  |  | 24 | Integrate the provided cruise API.
|  |  | Cruise booking form | https://prnt.sc/hdlmqd |  | 8 | Same as tranfer booking form
|  |  | Booking process |  |  | 8 | Use the booking process same as hotel
|  | Tours | Search result | http://prntscr.com/hg5wnc |  | 8 | Integrate the Tours search box. We will also pull the tour data from API.
|  |  | Tour API Integration |  |  | 25 | Integrate the provided tour API.
|  |  | Tour details display in single selection | http://prntscr.com/hg4jlh |  | 32 | Display the selected tour information with check availablititty feature and it depends on API data.
|  |  | After selection and display price | http://prntscr.com/hg4kx1 |  | 8 | Provide the edit availablity feature
Tour Home Page | http://prntscr.com/hg5w4z |  | Details about the tour | http://prntscr.com/hg62zd |  | 16 | Display the tour details which we will pull from API.
|  |  | Tour available checked and process | http://prntscr.com/hdllhz |  | NA | same as edit availablity
|  |  | Tour book form | http://prntscr.com/hdlltx |  | 8
|  |  | Booking process |  |  | 8 | Use the booking process same as hotel
|  | Packages | Meta addon Duration | Single tour infomations display as accoundion on/off as show/hide |  | TBD | We will discuss this section
|  |  | Like Activities | This category include package tour list |  | TBD
Account |  | Profile |  | http://prntscr.com/hdlnq1 |  | 8
|  | Booked data | Search | http://prntscr.com/hdlnuq |  | 12 | Booking search option
|  |  | Result & history | http://prntscr.com/hdlo7l |  | 24 | Booking list & Detail
|  | Agency detail |  | http://prntscr.com/hdlnxk |  | 8 | Update agency detail information
|  | Multi login user |  | http://prntscr.com/hdlo1d |  | 8 | Admin can add multiple users in single agency
|  | Edit password |  | Move to profile section |  | 4
Price rules |  | Adult |  | 100% |  | TBD
|  | Child 1-2yrs |  | 15% |  | TBD
|  | Child 3-12yrs |  | 75% |  | TBD
Agent Commission |  | Commission | Commission per book | 12% |  | 8 | Update the agent commission which we will add in booking
Payment |  | Manual payment | Bank transfer | 88% |  | TBD
|  |  | Enett | 88% |  | TBD
|  | Automatic payment | API Commweb checkout | 100% |  | TBD
Website Design
PSDs & xHTML | [5 empty] | 80 | We will create the design according to the provided layout.
Backend
|  | Backend Login and Dashboard |  |  |  | 4
Currencies |  | Manage Currency |  |  |  | 8 | Create the currency master to manager the currency from admin.
|  | Manage Super Deals Section |  |  |  | 8 | Create the section to upload the deals with link.
|  | Manage Search Destination |  |  |  | 4 | Admin will add the multiple destination which we will display in frontend
|  | Hotel Manager |  |  |  | 20 | Admin can update the hotel information and mark the flag as popular to display on accomodation page.
|  | Curise Master |  |  |  | 8 | Manage the cruise master which we will display on top menu.
|  | Manage Agency Users |  |  |  | 16 | Admin can add the agency details and send the login details for frontend.
|  | Manage Agent Commission |  |  |  | 4
|  | Manage Bookings |  |  |  | 16 | Display the booking and quote list
|  | Booking Reports |  |  |  | 26 | Create the booking reports as how many booking paid, how much amount is pending. Total confirmed bookings.
|  |  |  | Total Hours with Single Developer |  | 880 Man Hours
|  |  |  | Total Weeks with Single Developer |  | 22 Man Weeks
|  |  |  | Total Weeks with Two Developers |  | 12 Man Weeks

## Back-end (hidden)
Subjects | Functions | Short Description
Input Data | Manual
Booking | Report
Commission | Manual + Commission history
Payment | Manual + Auto
User
Analytics | Report